## Corridor Work
Corridor | Section | Identifier | Task Group | Work Breakdown | Size | Planned | Actual | Progress (%)
West | S1 | main road | Excavation | Barrier | na | 347 | 0 | 0
West | S1 | main road | Excavation | Pavement Cutting | na | 347 | 0 | 0
West | S1 | main road | Excavation | Excavation | W3xD3.4 | 347 | 0 | 0
West | S1 | main road | Utility Laying | DNCC Drainage | 1200mm | 347 | 0 | 0
West | S1 | main road | Utility Laying | DWASA | 315mm | 347 | 0 | 0
West | S1 | main road | Utility Laying | DWASA | 800mm | 347 | 0 | 0
West | S1 | main road | Utility Laying | TITAS | 200mm | 347 | 0 | 0
West | S1 | main road | Utility Laying | Pvt. Ducts | na | 347 | 0 | 0
West | S1 | main road | Utility Laying | BTCL | na | 347 | 0 | 0
West | S1 | main road | Utility Laying | PGCB | 132kV | 347 | 0 | 0
West | S1 | main road | Road Reinstatement | Sub-Base | na | 347 | 0 | 0
West | S1 | main road | Road Reinstatement | Base | na | 347 | 0 | 0
West | S1 | main road | Road Reinstatement | Ashphalt | na | 347 | 0 | 0
West | S4-1 | secondary road | Excavation | Barrier | na | 54 | 0 | 0
West | S4-1 | secondary road | Excavation | Pavement Cutting | na | 54 | 0 | 0
West | S4-1 | secondary road | Excavation | Excavation | na | 54 | 0 | 0
West | S4-1 | secondary road | Utility Laying | DNCC Drainage | 1200mm | 54 | 0 | 0
West | S4-1 | secondary road | Utility Laying | DWASA | 75mm | 54 | 0 | 0
West | S4-1 | secondary road | Utility Laying | DWASA | 75mm | 54 | 0 | 0
West | S4-1 | secondary road | Utility Laying | DWASA | 315mm | 54 | 0 | 0
West | S4-1 | secondary road | Utility Laying | DESCO | 11kV | 54 | 0 | 0
West | S4-1 | secondary road | Utility Laying | Pvt. Ducts | na | 54 | 0 | 0
West | S4-1 | secondary road | Utility Laying | BTCL | na | 54 | 0 | 0
West | S4-1 | secondary road | Road Reinstatement | Sub-Base | na | 54 | 0 | 0
West | S4-1 | secondary road | Road Reinstatement | Base | na | 54 | 0 | 0
West | S4-1 | secondary road | Road Reinstatement | Ashphalt | na | 54 | 0 | 0
West | S4-2 | secondary road | Excavation | Barrier | na | 293 | 0 | 0
West | S4-2 | secondary road | Excavation | Pavement Cutting | na | 293 | 0 | 0
West | S4-2 | secondary road | Excavation | Excavation | W0.7xD1.9 | 293 | 0 | 0
West | S4-2 | secondary road | Utility Laying | DWASA | 75mm | 293 | 0 | 0
West | S4-2 | secondary road | Utility Laying | TITAS | 50mm | 293 | 0 | 0
West | S4-2 | secondary road | Road Reinstatement | Sub-Base | na | 293 | 0 | 0
West | S4-2 | secondary road | Road Reinstatement | Base | na | 293 | 0 | 0
West | S4-2 | secondary road | Road Reinstatement | Ashphalt | na | 293 | 0 | 0
East | S2 | main road | Excavation | Barrier | na | 321 | 0 | 0
East | S2 | main road | Excavation | Pavement Cutting | na | 321 | 0 | 0
East | S2 | main road | Excavation | Excavation | na | 321 | 0 | 0
East | S2 | main road | Utility Laying | DNCC Drainage | 1524mm | 321 | 0 | 0
East | S2 | main road | Utility Laying | DNCC Drainage | 1000mm | 121 | 0 | 0
East | S2 | main road | Utility Laying | DWASA | 160mm | 121 | 0 | 0
East | S2 | main road | Utility Laying | DWASA | 450mm | 321 | 0 | 0
East | S2 | main road | Utility Laying | TITAS | 400mm | 321 | 0 | 0
East | S2 | main road | Utility Laying | DESCO | na | 321 | 0 | 0
East | S2 | main road | Utility Laying | BTCL | na | 321 | 0 | 0
East | S2 | main road | Road Reinstatement | Sub-Base | na | 321 | 0 | 0
East | S2 | main road | Road Reinstatement | Base | na | 321 | 0 | 0
East | S2 | main road | Road Reinstatement | Ashphalt | na | 321 | 0 | 0
East | S3 | main road | Excavation | Barrier | na | 200 | 0 | 0
East | S3 | main road | Excavation | Pavement Cutting | na | 200 | 0 | 0
East | S3 | main road | Excavation | Excavation | W1.0xD2.2 | 200 | 0 | 0
East | S3 | main road | Utility Laying | DNCC Drainage | 1000mm | 67 | 0 | 0
East | S3 | main road | Utility Laying | DWASA | 200mm | 200 | 0 | 0
East | S3 | main road | Utility Laying | TITAS | 150mm | 200 | 0 | 0
East | S3 | main road | Utility Laying | DESCO | 11kV | 200 | 0 | 0
East | S3 | main road | Road Reinstatement | Sub-Base | na | 200 | 0 | 0
East | S3 | main road | Road Reinstatement | Base | na | 200 | 0 | 0
East | S3 | main road | Road Reinstatement | Ashphalt | na | 200 | 0 | 0
South Crossing | S5 | main road | Excavation | Steel Plate | na | 16 | 0 | 0
South Crossing | S5 | main road | Excavation | Pavement Cutting | na | 16 | 0 | 0
South Crossing | S5 | main road | Excavation | Excavation | W3.1xD3.0 | 16 | 0 | 0
South Crossing | S5 | main road | Utility Laying | DNCC Drainage | check | 16 | 0 | 0
South Crossing | S5 | main road | Utility Laying | DWASA | check | 16 | 0 | 0
South Crossing | S5 | main road | Road Reinstatement | Sub-Base | na | 16 | 0 | 0
South Crossing | S5 | main road | Road Reinstatement | Base | na | 16 | 0 | 0
South Crossing | S5 | main road | Road Reinstatement | Ashphalt | na | 16 | 0 | 0

## Progress
Date | Baseline | Actual
2024-04-10 | 0 | 0.5
2024-04-11 | 1.5 | 0.5
2024-04-12 | 2.9 | 0.5
2024-04-13 | 3.6 | 0.5
2024-04-14 | 4.3 | 0.5
2024-04-15 | 5.9 | 0.5
2024-04-16 | 7.5 | 0.5
2024-04-17 | 8.8 | 0.5
2024-04-18 | 9.4 | 0.5
2024-04-19 | 9.6 | 0.5
2024-04-20 | 9.9 | 0.5
2024-04-21 | 10.2 | 0.5
2024-04-22 | 10.8 | 0.5
2024-04-23 | 11.6 | 0.5
2024-04-24 | 12.5 | 0.5
2024-04-25 | 13.2 | 0.5
2024-04-26 | 14 | 0.5
2024-04-27 | 14.8 | 0.5
2024-04-28 | 15.4 | 0.5
2024-04-29 | 15.8 | 0.5
2024-04-30 | 16.7 | 0.5
2024-05-01 | 17.8 | 0.5
2024-05-02 | 18.9 | 0.5
2024-05-03 | 19.8 | 0.5
2024-05-04 | 20.8 | 0.5
2024-05-05 | 21.8 | 0.5
2024-05-06 | 23 | 0.5
2024-05-07 | 24.2 | 0.5
2024-05-08 | 25.6 | 0.5
2024-05-09 | 27.1 | 0.5
2024-05-10 | 28.7 | 0.5
2024-05-11 | 30.3 | 0.5
2024-05-12 | 31.8 | 0.5
2024-05-13 | 33.3 | 0.5
2024-05-14 | 33.9 | 0.5
2024-05-15 | 34.4 | 0.5
2024-05-16 | 35.2 | 0.5
2024-05-17 | 36.2 | 0.5
2024-05-18 | 37.1 | 0.5
2024-05-19 | 37.9 | 0.5
2024-05-20 | 39.2 | 0.5
2024-05-21 | 40.5 | 0.5
2024-05-22 | 41.9 | 0.5
2024-05-23 | 43.4 | 0.5
2024-05-24 | 45 | 0.5
2024-05-25 | 46.7 | 0.5
2024-05-26 | 47.7 | 0.5
2024-05-27 | 48.9 | 0.5
2024-05-28 | 52.1 | 0.5
2024-05-29 | 52.8 | 0.5
2024-05-30 | 53.5 | 0.5
2024-05-31 | 54.3 | 0.5
2024-06-01 | 55.1 | 0.5
2024-06-02 | 55.8 | 0.5
2024-06-03 | 56.6 | 0.5
2024-06-04 | 57.4 | 0.5
2024-06-05 | 58.1 | 0.5
2024-06-06 | 58.9 | 0.5
2024-06-07 | 59.6 | 0.5
2024-06-08 | 60.3 | 0.5
2024-06-09 | 60.9 | 0.5
2024-06-10 | 61.5 | 0.5
2024-06-11 | 62.2 | 0.5
2024-06-12 | 62.8 | 0.5
2024-06-13 | 63.5 | 0.5
2024-06-14 | 64.1 | 0.5
2024-06-15 | 64.7 | 0.5
2024-06-16 | 65.3 | 0.5
2024-06-17 | 65.8 | 0.5
2024-06-18 | 67.1 | 0.5
2024-06-19 | 68.4 | 0.5
2024-06-20 | 69.4 | 0.5
2024-06-21 | 70.3 | 0.5
2024-06-22 | 71.2 | 0.5
2024-06-23 | 71.7 | 0.5
2024-06-24 | 72.3 | 0.5
2024-06-25 | 72.8 | 0.5
2024-06-26 | 73.3 | 0.5
2024-06-27 | 74.1 | 0.5
2024-06-28 | 74.8 | 0.5
2024-06-29 | 75.6 | 0.5
2024-06-30 | 76.4 | 0.5
2024-07-01 | 77.1 | 0.5
2024-07-02 | 77.9 | 0.5
2024-07-03 | 78.7 | 0.5
2024-07-04 | 79.3 | 0.5
2024-07-05 | 79.8 | 0.5
2024-07-06 | 79.9 | 0.5
2024-07-07 | 80 | 0.5
2024-07-08 | 80.1 | 0.5
2024-07-09 | 80.2 | 0.5
2024-07-10 | 80.3 | 0.5
2024-07-11 | 80.4 | 0.5
2024-07-12 | 80.5 | 0.5
2024-07-13 | 80.6 | 0.5
2024-07-14 | 81 | 0.5
2024-07-15 | 81.3 | 0.5
2024-07-16 | 81.7 | 0.5
2024-07-17 | 82.1 | 0.5
2024-07-18 | 82.4 | 0.5
2024-07-19 | 82.6 | 0.5
2024-07-20 | 82.9 | 0.5
2024-07-21 | 83 | 0.5
2024-07-22 | 83.3 | 0.5
2024-07-23 | 83.7 | 0.5
2024-07-24 | 84 | 0.5
2024-07-25 | 84.4 | 0.5
2024-07-26 | 84.7 | 0.5
2024-07-27 | 85 | 0.5
2024-07-28 | 85.4 | 0.5
2024-07-29 | 85.4 | 0.5
2024-07-30 | 85.6 | 0.5
2024-07-31 | 85.9 | 0.5
2024-08-01 | 86.2 | 0.5
2024-08-02 | 86.4 | 0.5
2024-08-03 | 86.7 | 0.5
2024-08-04 | 87 | 0.5
2024-08-05 | 87 | 0.5
2024-08-06 | 87 | 0.5
2024-08-07 | 87.3 | 0.5
2024-08-08 | 87.5 | 0.5
2024-08-09 | 87.7 | 0.5
2024-08-10 | 88 | 0.5
2024-08-11 | 88.2 | 0.5
2024-08-12 | 88.5 | 0.5
2024-08-13 | 88.7 | 0.5
2024-08-14 | 88.9 | 0.5
2024-08-15 | 89.2 | 0.5
2024-08-16 | 89.4 | 0.5
2024-08-17 | 89.7 | 0.5
2024-08-18 | 89.9 | 0.5
2024-08-19 | 90.1 | 0.5
2024-08-20 | 90.4 | 0.5
2024-08-21 | 90.9 | 0.5
2024-08-22 | 91.5 | 0.5
2024-08-23 | 92 | 0.5
2024-08-24 | 92.6 | 0.5
2024-08-25 | 92.7 | 0.5
2024-08-26 | 92.9 | 0.5
2024-08-27 | 93.1 | 0.5
2024-08-28 | 93.4 | 0.5
2024-08-29 | 93.6 | 0.5
2024-08-30 | 93.9 | 0.5
2024-08-31 | 94.1 | 0.5
2024-09-01 | 94.3 | 0.5
2024-09-02 | 94.4 | 0.5
2024-09-03 | 94.6 | 0.5
2024-09-04 | 94.7 | 0.5
2024-09-05 | 94.8 | 0.5
2024-09-06 | 95 | 0.5
2024-09-07 | 95.1 | 0.5
2024-09-08 | 95.3 | 0.5
2024-09-09 | 95.4 | 0.5
2024-09-10 | 95.4 | 0.5
2024-09-11 | 95.4 | 0.5
2024-09-12 | 95.4 | 0.5
2024-09-13 | 95.4 | 0.5
2024-09-14 | 95.4 | 0.5
2024-09-15 | 95.4 | 0.5
2024-09-16 | 95.8 | 0.5
2024-09-17 | 96.1 | 0.5
2024-09-18 | 96.4 | 0.5
2024-09-19 | 96.7 | 0.5
2024-09-20 | 97 | 0.5
2024-09-21 | 97.4 | 0.5
2024-09-22 | 97.7 | 0.5
2024-09-23 | 97.8 | 0.5
2024-09-24 | 98 | 0.5
2024-09-25 | 98.1 | 0.5
2024-09-26 | 98.2 | 0.5
2024-09-27 | 98.4 | 0.5
2024-09-28 | 98.5 | 0.5
2024-09-29 | 98.6 | 0.5
2024-09-30 | 98.7 | 0.5
2024-10-01 | 98.9 | 0.5
2024-10-02 | 99.1 | 0.5
2024-10-03 | 99.4 | 0.5
2024-10-04 | 99.7 | 0.5
2024-10-05 | 100 | 0.5
2024-10-06 | 100 | 0.5
2024-10-07 | 100 | 0.5
2024-10-08 | 100 | 0.5
2024-10-09 | 100 | 0.5
2024-10-10 | 100 | 0.5
2024-10-11 | 100 | 0.5

## Issue Log
Issue ID | Corridor | Description | Status | Created on | Resolved on
1 | East | Delay in excavation due to rain | Pending | 2025-01-02 | 2025-02-02
2 | West | Gas pipe leakage detected | Solved | 2025-01-03 | 2025-02-03
3 | Cross | Water supply pipe damaged | Pending | 2025-01-04 | 2025-02-04
4 | East | Equipment shortage | Pending | 2025-01-05 | 2025-02-05
5 | West | Gas pipe installation complete | Solved | 2025-01-06 | 2025-02-06

## images
image
s05/plan.jpg
s05/HA1-HA1'.jpg
s05/HA2-HA2'.jpg
s05/HA3-HA3'.jpg
s05/HA4-HA4'.jpg
s05/C12-C12'.jpg
s05/C13-C13'.jpg
s05/C13A-C13A'.jpg
s05/C13B-C13B'.jpg

## Status
ID | Subject | Description | Date
1 | Trial Pit