## Corridor Work
Corridor | Section | Identifier | Task Group | Work Breakdown | Size | Planned | Actual | Progress (%)
West | 1 | main road | Excavation | Barrier | na | 460 | 460 | 100
West | 1 | main road | Excavation | Pavement Cutting | na | 460 | 460 | 100
West | 1 | main road | Excavation | Excavation | na | 460 | 460 | 100
West | 1 | main road | Utility Laying | DNCC Drainage | 750mm | 460 | 460 | 100
West | 1 | main road | Utility Laying | DWASA | 315mm | 440 | 440 | 100
West | 1 | main road | Utility Laying | DWASA | 200mm | 130 | 130 | 100
West | 1 | main road | Utility Laying | TITAS | 200mm | 440 | 440 | 100
West | 1 | main road | Utility Laying | Pvt. Communication Cable | na | 440 | 440 | 100
West | 1 | main road | Utility Laying | BTCL | na | 440 | 440 | 100
West | 1 | main road | Road Reinstatement | Sub-Base | na | 440 | 100 | 22.7273
West | 1 | main road | Road Reinstatement | Base | na | 440 | 0 | 0
West | 1 | main road | Road Reinstatement | Ashphalt | na | 440 | 0 | 0
West | 5 | secondary road | Excavation | Barrier | na | 52 | 52 | 100
West | 5 | secondary road | Excavation | Pavement Cutting | na | 52 | 52 | 100
West | 5 | secondary road | Excavation | Excavation | na | 52 | 52 | 100
West | 5 | secondary road | Utility Laying | DNCC Drainage | 750mm | 52 | 52 | 100
West | 5 | secondary road | Utility Laying | DWASA | 315mm | 52 | 52 | 100
West | 5 | secondary road | Utility Laying | TITAS | 200mm | 52 | 52 | 100
West | 5 | secondary road | Utility Laying | Pvt. Communication Cable | na | 52 | 52 | 100
West | 5 | secondary road | Utility Laying | BTCL | na | 52 | 52 | 100
West | 5 | secondary road | Road Reinstatement | Sub-Base | na | 52 | 10 | 19.2308
West | 5 | secondary road | Road Reinstatement | Base | na | 52 | 0 | 0
West | 5 | secondary road | Road Reinstatement | Ashphalt | na | 52 | 0 | 0
East | 2 | main road | Excavation | Barrier | na | 260 | 260 | 100
East | 2 | main road | Excavation | Pavement Cutting | na | 260 | 260 | 100
East | 2 | main road | Excavation | Excavation | na | 260 | 260 | 100
East | 2 | main road | Utility Laying | DNCC Drainage | 750mm | 260 | 260 | 100
East | 2 | main road | Utility Laying | DWASA | 315mm | 260 | 260 | 100
East | 2 | main road | Utility Laying | DWASA | 200mm | 260 | 260 | 100
East | 2 | main road | Utility Laying | TITAS | 400mm | 260 | 260 | 100
East | 2 | main road | Utility Laying | Pvt. Communication Cable | na | 260 | 260 | 100
East | 2 | main road | Utility Laying | BTCL | na | 260 | 260 | 100
East | 2 | main road | Road Reinstatement | Sub-Base | na | 260 | 60 | 23.0769
East | 2 | main road | Road Reinstatement | Base | na | 260 | 0 | 0
East | 2 | main road | Road Reinstatement | Ashphalt | na | 260 | 0 | 0
East | 4 | main road | Excavation | Barrier | na | 180 | 180 | 100
East | 4 | main road | Excavation | Pavement Cutting | na | 180 | 180 | 100
East | 4 | main road | Excavation | Excavation | na | 180 | 180 | 100
East | 4 | main road | Utility Laying | DNCC Drainage | 750mm | 180 | 180 | 100
East | 4 | main road | Utility Laying | DWASA | 315mm | 180 | 180 | 100
East | 4 | main road | Utility Laying | TITAS | 200mm | 180 | 180 | 100
East | 4 | main road | Utility Laying | TITAS | 400mm | 180 | 100 | 55.5556
East | 4 | main road | Utility Laying | Pvt. Communication Cable | na | 180 | 180 | 100
East | 4 | main road | Utility Laying | BTCL | na | 180 | 180 | 100
East | 4 | main road | Road Reinstatement | Sub-Base | na | 180 | 0 | 0
East | 4 | main road | Road Reinstatement | Base | na | 180 | 0 | 0
East | 4 | main road | Road Reinstatement | Ashphalt | na | 180 | 0 | 0
East | 7 | Bashundhara road | Excavation | Barrier | na | 52 | 52 | 100
East | 7 | Bashundhara road | Excavation | Pavement Cutting | na | 52 | 52 | 100
East | 7 | Bashundhara road | Excavation | Excavation | na | 52 | 52 | 100
East | 7 | Bashundhara road | Utility Laying | DNCC Drainage | 750mm | 52 | 52 | 100
East | 7 | Bashundhara road | Utility Laying | DWASA | 315mm | 52 | 52 | 100
East | 7 | Bashundhara road | Utility Laying | TITAS | 200mm | 52 | 52 | 100
East | 4 | main road | Utility Laying | TITAS | 400mm | 52 | 52 | 100
East | 7 | Bashundhara road | Utility Laying | Pvt. Communication Cable | na | 52 | 52 | 100
East | 7 | Bashundhara road | Utility Laying | BTCL | na | 52 | 52 | 100
East | 7 | Bashundhara road | Road Reinstatement | Sub-Base | na | 52 | 10 | 19.2308
East | 7 | Bashundhara road | Road Reinstatement | Base | na | 52 | 0 | 0
East | 7 | Bashundhara road | Road Reinstatement | Ashphalt | na | 52 | 0 | 0

## Progress
Date | Baseline | Actual
2024-09-28 | 0 | 1.8
2024-09-29 | 1.5 | 1.8
2024-09-30 | 2.9 | 1.8
2024-10-01 | 3.6 | 1.8
2024-10-02 | 4.3 | 1.8
2024-10-03 | 5.9 | 1.8
2024-10-04 | 7.5 | 1.8
2024-10-05 | 8.8 | 1.8
2024-10-06 | 9.4 | 3.7
2024-10-07 | 9.6 | 3.7
2024-10-08 | 9.9 | 3.7
2024-10-09 | 10.2 | 3.7
2024-10-10 | 10.8 | 4.6
2024-10-11 | 11.6 | 4.6
2024-10-12 | 12.5 | 4.6
2024-10-13 | 13.2 | 4.6
2024-10-14 | 14 | 4.6
2024-10-15 | 14.8 | 4.6
2024-10-16 | 15.4 | 4.6
2024-10-17 | 15.8 | 4.6
2024-10-18 | 16.7 | 4.6
2024-10-19 | 17.8 | 4.6
2024-10-20 | 18.9 | 4.6
2024-10-21 | 19.8 | 4.6
2024-10-22 | 20.8 | 4.6
2024-10-23 | 21.8 | 5.7
2024-10-24 | 23 | 5.7
2024-10-25 | 24.2 | 5.7
2024-10-26 | 25.6 | 5.7
2024-10-27 | 27.1 | 5.7
2024-10-28 | 28.7 | 5.7
2024-10-29 | 30.3 | 5.7
2024-10-30 | 31.8 | 5.7
2024-10-31 | 33.3 | 6.7
2024-11-01 | 33.9 | 7.6
2024-11-02 | 34.4 | 7.9
2024-11-03 | 35.2 | 9.1
2024-11-04 | 36.2 | 9.1
2024-11-05 | 37.1 | 9.1
2024-11-06 | 37.9 | 9.1
2024-11-07 | 39.2 | 10.3
2024-11-08 | 40.5 | 10.4
2024-11-09 | 41.9 | 10.5
2024-11-10 | 43.4 | 11.1
2024-11-11 | 45 | 18.9
2024-11-12 | 46.7 | 19.3
2024-11-13 | 47.7 | 19.6
2024-11-14 | 48.9 | 19.9
2024-11-15 | 52.1 | 20.4
2024-11-16 | 52.8 | 20.8
2024-11-17 | 53.5 | 21.3
2024-11-18 | 54.3 | 21.8
2024-11-19 | 55.1 | 22.3
2024-11-20 | 55.8 | 22.6
2024-11-21 | 56.6 | 22.9
2024-11-22 | 57.4 | 23.1
2024-11-23 | 58.1 | 23.2
2024-11-24 | 58.9 | 23.3
2024-11-25 | 59.6 | 23.5
2024-11-26 | 60.3 | 23.7
2024-11-27 | 60.9 | 23.9
2024-11-28 | 61.5 | 24.1
2024-11-29 | 62.2 | 25.2
2024-11-30 | 62.8 | 25.6
2024-12-01 | 63.5 | 26
2024-12-02 | 64.1 | 26.3
2024-12-03 | 64.7 | 26.5
2024-12-04 | 65.3 | 26.8
2024-12-05 | 65.8 | 26.9
2024-12-06 | 67.1 | 27.3
2024-12-07 | 68.4 | 27.5
2024-12-08 | 69.4 | 27.6
2024-12-09 | 70.3 | 27.7
2024-12-10 | 71.2 | 29.4
2024-12-11 | 71.7 | 29.6
2024-12-12 | 72.3 | 29.8
2024-12-13 | 72.8 | 30.4
2024-12-14 | 73.3 | 31
2024-12-15 | 74.1 | 31.3
2024-12-16 | 74.8 | 31.5
2024-12-17 | 75.6 | 31.9
2024-12-18 | 76.4 | 33.2
2024-12-19 | 77.1 | 33.4
2024-12-20 | 77.9 | 33.7
2024-12-21 | 78.7 | 34.1
2024-12-22 | 79.3 | 34.3
2024-12-23 | 79.8 | 34.5
2024-12-24 | 79.9 | 34.7
2024-12-25 | 80 | 34.8
2024-12-26 | 80.1 | 35
2024-12-27 | 80.2 | 35.4
2024-12-28 | 80.3 | 35.9
2024-12-29 | 80.4 | 37.6
2024-12-30 | 80.5 | 39.2
2024-12-31 | 80.6 | 40.3
2025-01-01 | 81 | 41.2
2025-01-02 | 81.3 | 42.2
2025-01-03 | 81.7 | 43.9
2025-01-04 | 82.1 | 45.2
2025-01-05 | 82.4 | 46.5
2025-01-06 | 82.6 | 47.7
2025-01-07 | 82.9 | 48.2
2025-01-08 | 83 | 48.9
2025-01-09 | 83.3 | 50
2025-01-10 | 83.7 | 51
2025-01-11 | 84 | 51.9
2025-01-12 | 84.4 | 54.3
2025-01-13 | 84.7 | 55
2025-01-14 | 85 | 55.5
2025-01-15 | 85.4 | 56
2025-01-16 | 85.4 | 56.2
2025-01-17 | 85.6 | 56.6
2025-01-18 | 85.9 | 57
2025-01-19 | 86.2 | 57.5
2025-01-20 | 86.4 | 57.9
2025-01-21 | 86.7 | 58.4
2025-01-22 | 87 | 58.9
2025-01-23 | 87 | 59.3
2025-01-24 | 87 | 60
2025-01-25 | 87.3 | 60.8
2025-01-26 | 87.5 | 62.5
2025-01-27 | 87.7 | 64.2
2025-01-28 | 88 | 66.2
2025-01-29 | 88.2 | 67.5
2025-01-30 | 88.5 | 68.3
2025-01-31 | 88.7 | 69.1
2025-02-01 | 88.9 | 70
2025-02-02 | 89.2 | 70.9
2025-02-03 | 89.4 | 71.8
2025-02-04 | 89.7 | 72.7
2025-02-05 | 89.9 | 73
2025-02-06 | 90.1 | 73.1
2025-02-07 | 90.4 | 73.2
2025-02-08 | 90.9 | 73.3
2025-02-09 | 91.5 | 73.4
2025-02-10 | 92 | 73.6
2025-02-11 | 92.6 | 74.3
2025-02-12 | 92.7 | 74.9
2025-02-13 | 92.9 | 75.6
2025-02-14 | 93.1 | 76.5
2025-02-15 | 93.4 | 77.4
2025-02-16 | 93.6 | 77.6
2025-02-17 | 93.9 | 77.9
2025-02-18 | 94.1 | 78.3
2025-02-19 | 94.3 | 78.6
2025-02-20 | 94.4 | 78.9
2025-02-21 | 94.6 | 79.2
2025-02-22 | 94.7 | 79.6
2025-02-23 | 94.8 | 79.9
2025-02-24 | 95 | 80.6
2025-02-25 | 95.1 | 81.3
2025-02-26 | 95.3 | 82.1
2025-02-27 | 95.4 | 83
2025-02-28 | 95.4 | 83.2
2025-03-01 | 95.4 | 83.4
2025-03-02 | 95.4 | 83.6
2025-03-03 | 95.4 | 83.7
2025-03-04 | 95.4 | 83.9
2025-03-05 | 95.4 | 84
2025-03-06 | 95.8 | 84.2
2025-03-07 | 96.1 | 84.3
2025-03-08 | 96.4 | 84.4
2025-03-09 | 96.7 | 84.4
2025-03-10 | 97 | 84.4
2025-03-11 | 97.4 | 84.4
2025-03-12 | 97.7 | 84.4
2025-03-13 | 97.8 | 84.4
2025-03-14 | 98 | 84.4
2025-03-15 | 98.1 | 84.4
2025-03-16 | 98.2 | 84.4
2025-03-17 | 98.4 | 84.4
2025-03-18 | 98.5 | 84.4
2025-03-19 | 98.6 | 84.4
2025-03-20 | 98.7 | 84.4
2025-03-21 | 98.9 | 84.4
2025-03-22 | 99.1 | 84.4
2025-03-23 | 99.4 | 84.4
2025-03-24 | 99.7 | 84.4
2025-03-25 | 100 | 84.4
2025-03-26 | 100 | 84.4
2025-03-27 | 100 | 84.4
2025-03-28 | 100 | 84.4
2025-03-29 | 100 | 84.4
2025-03-30 | 100 | 84.4
2025-03-31 | 100 | 84.4

## Remaining
Issue ID | Corridor | Description | Status
1 | East | TITAS 400mm explosive test | Pending
2 | East | TITAS 200mm explosive test | Pending
3 | East | TITAS shutdown & commissioning | Pending

## Issue Log
Issue ID | Corridor | Description | Status | Created on | Resolved on
1 | East | Delay in excavation due to rain | Pending | 2025-01-02 | 2025-02-02
2 | West | Gas pipe leakage detected | Solved | 2025-01-03 | 2025-02-03
3 | Cross | Water supply pipe damaged | Pending | 2025-01-04 | 2025-02-04
4 | East | Equipment shortage | Pending | 2025-01-05 | 2025-02-05
5 | West | Gas pipe installation complete | Solved | 2025-01-06 | 2025-02-06

## images
image | update_date
s05/plan.jpg | 2025-04-10
s05/HA1-HA1'.jpg | 2025-04-10
s05/HA2-HA2'.jpg | 2025-04-10
s05/HA3-HA3'.jpg | 2025-04-10
s05/HA4-HA4'.jpg | 2025-04-10
s05/C12-C12'.jpg | 2025-04-10
s05/C13-C13'.jpg | 2025-04-10
s05/C13A-C13A'.jpg | 2025-04-10
s05/C13B-C13B'.jpg | 2025-04-10