## Corridor Work
Corridor | Section | Identifier | Task Group | Work Breakdown | Size | Planned | Actual | Progress (%)
West | 1-1 | main road | Excavation | Barrier | na | 255 | 0 | 0
West | 1-1 | main road | Excavation | Pavement Cutting | na | 255 | 0 | 0
West | 1-1 | main road | Excavation | Excavation | na | 255 | 0 | 0
West | 1-1 | main road | Utility Laying | DNCC Drainage | 1524mm | 255 | 0 | 0
West | 1-1 | main road | Utility Laying | Pvt. Communication Cable | na | 255 | 0 | 0
West | 1-1 | main road | Utility Laying | BTCL | na | 255 | 0 | 0
West | 1-1 | main road | Utility Laying | DWASA | 110mm | 255 | 0 | 0
West | 1-1 | main road | Utility Laying | TITAS | 200mm | 255 | 0 | 0
West | 1-1 | main road | Utility Laying | DESCO | 33kV | 255 | 0 | 0
West | 1-1 | main road | Road Reinstatement | Sub-Base | na | 255 | 0 | 0
West | 1-1 | main road | Road Reinstatement | Base | na | 255 | 0 | 0
West | 1-1 | main road | Road Reinstatement | Ashphalt | na | 255 | 0 | 0
West | 1-2 | secondary road | Excavation | Barrier | na | 456 | 331 | 72.5877
West | 1-2 | secondary road | Excavation | Pavement Cutting | na | 456 | 331 | 72.5877
West | 1-2 | secondary road | Excavation | Excavation | na | 456 | 331 | 72.5877
West | 1-2 | secondary road | Utility Laying | DNCC Drainage | 1524mm | 456 | 18 | 3.9474
West | 1-2 | secondary road | Utility Laying | Pvt. Communication Cable | na | 456 | 0 | 0
West | 1-2 | secondary road | Utility Laying | BTCL | na | 456 | 0 | 0
West | 1-2 | secondary road | Utility Laying | TITAS | 200mm | 456 | 0 | 0
West | 1-2 | secondary road | Utility Laying | DWASA | 160mm | 456 | 0 | 0
West | 1-2 | secondary road | Utility Laying | DESCO | 132kV | 456 | 0 | 0
West | 1-2 | secondary road | Utility Laying | DESCO | 33kV | 456 | 0 | 0
West | 1-2 | secondary road | Road Reinstatement | Sub-Base | na | 456 | 0 | 0
West | 1-2 | secondary road | Road Reinstatement | Base | na | 456 | 0 | 0
West | 1-2 | main road | Road Reinstatement | Ashphalt | na | 456 | 0 | 0
East | 2-1 | main road | Excavation | Pavement Cutting | na | 260 | 0 | 0
East | 2-1 | main road | Excavation | Excavation | na | 260 | 0 | 0
East | 2-1 | main road | Utility Laying | DNCC Drainage | 750mm | 260 | 0 | 0
East | 2-1 | main road | Utility Laying | DWASA | 315mm | 260 | 0 | 0
East | 2-1 | main road | Utility Laying | DWASA | 200mm | 260 | 0 | 0
East | 2-1 | main road | Utility Laying | TITAS | 400mm | 260 | 0 | 0
East | 2-1 | main road | Utility Laying | Pvt. Communication Cable | na | 260 | 0 | 0
East | 2-1 | main road | Utility Laying | BTCL | na | 260 | 0 | 0
East | 2-1 | main road | Road Reinstatement | Sub-Base | na | 260 | 0 | 0
East | 2-1 | main road | Road Reinstatement | Base | na | 260 | 0 | 0
East | 2-1 | main road | Road Reinstatement | Ashphalt | na | 260 | 0 | 0
East | 2-1 | main road | Excavation | Barrier | na | 180 | 0 | 0
East | 2-1 | main road | Excavation | Pavement Cutting | na | 180 | 0 | 0
East | 2-1 | main road | Excavation | Excavation | na | 180 | 0 | 0
East | 2-1 | main road | Utility Laying | DNCC Drainage | 750mm | 180 | 0 | 0
East | 2-1 | main road | Utility Laying | DWASA | 315mm | 180 | 0 | 0
East | 2-1 | main road | Utility Laying | TITAS | 200mm | 180 | 0 | 0
East | 2-1 | main road | Utility Laying | TITAS | 400mm | 180 | 0 | 0
East | 2-1 | main road | Utility Laying | Pvt. Communication Cable | na | 180 | 0 | 0
East | 2-1 | main road | Utility Laying | BTCL | na | 180 | 0 | 0
East | 2-1 | main road | Road Reinstatement | Sub-Base | na | 180 | 0 | 0
East | 2-1 | main road | Road Reinstatement | Base | na | 180 | 0 | 0
East | 2-1 | main road | Road Reinstatement | Ashphalt | na | 180 | 0 | 0
East | 2-1 | Bashundhara road | Excavation | Barrier | na | 52 | 0 | 0
East | 2-1 | Bashundhara road | Excavation | Pavement Cutting | na | 52 | 0 | 0
East | 2-1 | Bashundhara road | Excavation | Excavation | na | 52 | 0 | 0
East | 2-1 | Bashundhara road | Utility Laying | DNCC Drainage | 750mm | 52 | 0 | 0
East | 2-1 | Bashundhara road | Utility Laying | DWASA | 315mm | 52 | 0 | 0
East | 2-1 | Bashundhara road | Utility Laying | TITAS | 200mm | 52 | 0 | 0
East | 2-1 | main road | Utility Laying | TITAS | 400mm | 52 | 0 | 0
East | 2-1 | Bashundhara road | Utility Laying | Pvt. Communication Cable | na | 52 | 0 | 0
East | 2-1 | Bashundhara road | Utility Laying | BTCL | na | 52 | 0 | 0
East | 2-1 | Bashundhara road | Road Reinstatement | Sub-Base | na | 52 | 0 | 0
East | 2-1 | Bashundhara road | Road Reinstatement | Base | na | 52 | 0 | 0
East | 2-1 | Bashundhara road | Road Reinstatement | Ashphalt | na | 52 | 0 | 0

## Progress
Date | Baseline | Actual
2024-12-01 | 0 | 0
2024-12-02 | 0.1 | 0
2024-12-03 | 0.3 | 0
2024-12-04 | 0.4 | 0
2024-12-05 | 0.5 | 0
2024-12-06 | 0.7 | 0
2024-12-07 | 0.8 | 0
2024-12-08 | 1 | 0
2024-12-09 | 1.1 | 0
2024-12-10 | 1.3 | 0
2024-12-11 | 1.5 | 0
2024-12-12 | 1.6 | 0
2024-12-13 | 1.8 | 0
2024-12-14 | 1.9 | 0
2024-12-15 | 2.1 | 0
2024-12-16 | 2.3 | 0
2024-12-17 | 2.4 | 0
2024-12-18 | 2.6 | 0
2024-12-19 | 2.8 | 0
2024-12-20 | 2.9 | 0
2024-12-21 | 3.1 | 0
2024-12-22 | 3.3 | 0
2024-12-23 | 3.4 | 0
2024-12-24 | 3.6 | 0
2024-12-25 | 3.7 | 0
2024-12-26 | 3.9 | 0
2024-12-27 | 4.2 | 0
2024-12-28 | 4.5 | 0
2024-12-29 | 4.8 | 0
2024-12-30 | 5.1 | 0
2024-12-31 | 5.4 | 0
2025-01-01 | 5.7 | 0
2025-01-02 | 6.1 | 0
2025-01-03 | 6.4 | 0
2025-01-04 | 6.7 | 0
2025-01-05 | 7 | 0
2025-01-06 | 8 | 0
2025-01-07 | 8.9 | 0
2025-01-08 | 9.9 | 0
2025-01-09 | 10.8 | 0
2025-01-10 | 11.7 | 0
2025-01-11 | 12.7 | 0
2025-01-12 | 13.8 | 0
2025-01-13 | 15.2 | 0
2025-01-14 | 16.7 | 0
2025-01-15 | 18.4 | 0.1
2025-01-16 | 20.1 | 0.1
2025-01-17 | 21.4 | 0.1
2025-01-18 | 22.7 | 0.1
2025-01-19 | 23.8 | 0.1
2025-01-20 | 25 | 0.2
2025-01-21 | 26.1 | 0.2
2025-01-22 | 27.2 | 0.2
2025-01-23 | 28.7 | 0.2
2025-01-24 | 30.1 | 0.2
2025-01-25 | 31 | 0.2
2025-01-26 | 31.8 | 0.2
2025-01-27 | 32.6 | 0.3
2025-01-28 | 33.6 | 0.3
2025-01-29 | 34.6 | 0.3
2025-01-30 | 35.6 | 0.4
2025-01-31 | 36.6 | 0.5
2025-02-01 | 37.8 | 0.6
2025-02-02 | 38.8 | 0.7
2025-02-03 | 40 | 0.8
2025-02-04 | 41.3 | 0.9
2025-02-05 | 42.8 | 1
2025-02-06 | 44.3 | 1
2025-02-07 | 45.9 | 1.1
2025-02-08 | 47.3 | 1.2
2025-02-09 | 48.6 | 1.3
2025-02-10 | 50.6 | 1.3
2025-02-11 | 53.2 | 1.3
2025-02-12 | 56 | 1.3
2025-02-13 | 58.4 | 1.3
2025-02-14 | 60.2 | 1.3
2025-02-15 | 62.4 | 1.3
2025-02-16 | 64.6 | 1.3
2025-02-17 | 66.5 | 1.4
2025-02-18 | 68.1 | 1.5
2025-02-19 | 69.3 | 1.5
2025-02-20 | 70.4 | 1.5
2025-02-21 | 71.6 | 1.5
2025-02-22 | 72.8 | 1.5
2025-02-23 | 74.1 | 1.5
2025-02-24 | 75.7 | 1.5
2025-02-25 | 77 | 1.5
2025-02-26 | 78.2 | 1.5
2025-02-27 | 79.7 | 1.5
2025-02-28 | 81 | 1.5
2025-03-01 | 81.9 | 1.5
2025-03-02 | 82.7 | 1.5
2025-03-03 | 83.8 | 1.5
2025-03-04 | 84.9 | 1.5
2025-03-05 | 86 | 1.6
2025-03-06 | 86.8 | 1.6
2025-03-07 | 87.5 | 1.6
2025-03-08 | 88.1 | 1.6
2025-03-09 | 88.2 | 1.6
2025-03-10 | 88.3 | 1.6
2025-03-11 | 88.4 | 1.6
2025-03-12 | 88.5 | 1.6
2025-03-13 | 88.5 | 1.7
2025-03-14 | 88.6 | 1.7
2025-03-15 | 88.6 | 1.8
2025-03-16 | 88.6 | 1.9
2025-03-17 | 88.6 | 2
2025-03-18 | 88.6 | 2
2025-03-19 | 88.6 | 2
2025-03-20 | 88.6 | 2
2025-03-21 | 88.7 | 2
2025-03-22 | 89.5 | 2
2025-03-23 | 90.4 | 2
2025-03-24 | 91.7 | 2
2025-03-25 | 92.9 | 2
2025-03-26 | 94.2 | 2
2025-03-27 | 95.4 | 2
2025-03-28 | 96.6 | 2
2025-03-29 | 97.8 | 2
2025-03-30 | 99 | 2
2025-03-31 | 100 | 2
2025-04-01 | 100 | 2
2025-04-02 | 100 | 2
2025-04-03 | 100 | 2
2025-04-04 | 100 | 2
2025-04-05 | 100 | 2
2025-04-06 | 100 | 2
2025-04-07 | 100 | 2
2025-04-08 | 100 | 2.1
2025-04-09 | 100 | 2.1
2025-04-10 | 100 | 2.1
2025-04-11 | 100 | 2.2
2025-04-12 | 100 | 2.2
2025-04-13 | 100 | 2.2
2025-04-14 | 100 | 2.2
2025-04-15 | 100 | 2.2
2025-04-16 | 100 | 2.2
2025-04-17 | 100 | 2.2
2025-04-18 | 100 | 2.2
2025-04-19 | 100 | 2.2
2025-04-20 | 100 | 2.2
2025-04-21 | 100 | 2.2
2025-04-22 | 100 | 2.2
2025-04-23 | 100 | 2.2
2025-04-24 | 100 | 2.2
2025-04-25 | 100 | 2.2
2025-04-26 | 100 | 2.2
2025-04-27 | 100 | 2.2
2025-04-28 | 100 | 2.2
2025-04-29 | 100 | 2.2
2025-04-30 | 100 | 2.2
2025-05-01 | 100 | 2.2
2025-05-02 | 100 | 2.2
2025-05-03 | 100 | 2.2
2025-05-04 | 100 | 2.2
2025-05-05 | 100 | 2.2
2025-05-06 | 100 | 2.2
2025-05-07 | 100 | 2.2
2025-05-08 | 100 | 2.2
2025-05-09 | 100 | 2.3
2025-05-10 | 100 | 2.3
2025-05-11 | 100 | 2.3
2025-05-12 | 100 | 2.3
2025-05-13 | 100 | 2.3
2025-05-14 | 100 | 2.4
2025-05-15 | 100 | 2.4
2025-05-16 | 100 | 2.4
2025-05-17 | 100 | 2.4
2025-05-18 | 100 | 2.5
2025-05-19 | 100 | 2.5
2025-05-20 | 100 | 2.5
2025-05-21 | 100 | 2.5
2025-05-22 | 100 | 2.5
2025-05-23 | 100 | 2.6
2025-05-24 | 100 | 2.6
2025-05-25 | 100 | 2.6
2025-05-26 | 100 | 2.6
2025-05-27 | 100 | 2.7
2025-05-28 | 100 | 2.7
2025-05-29 | 100 | 2.7
2025-05-30 | 100 | 2.7
2025-05-31 | 100 | 2.7
2025-06-01 | 100 | 2.8
2025-06-02 | 100 | 2.8
2025-06-03 | 100 | 2.8
2025-06-04 | 100 | 2.8
2025-06-05 | 100 | 2.8
2025-06-06 | 100 | 2.8
2025-06-07 | 100 | 2.8
2025-06-08 | 100 | 2.8
2025-06-09 | 100 | 2.8
2025-06-10 | 100 | 2.8
2025-06-11 | 100 | 2.8
2025-06-12 | 100 | 2.8
2025-06-13 | 100 | 2.8
2025-06-14 | 100 | 2.9
2025-06-15 | 100 | 2.9
2025-06-16 | 100 | 2.9
2025-06-17 | 100 | 2.9
2025-06-18 | 100 | 2.9
2025-06-19 | 100 | 2.9
2025-06-20 | 100 | 2.9
2025-06-21 | 100 | 2.9
2025-06-22 | 100 | 3
2025-06-23 | 100 | 3
2025-06-24 | 100 | 3.1
2025-06-25 | 100 | 3.1
2025-06-26 | 100 | 3.2
2025-06-27 | 100 | 3.2
2025-06-28 | 100 | 3.3
2025-06-29 | 100 | 3.3
2025-06-30 | 100 | 3.3
2025-07-01 | 100 | 3.3
2025-07-02 | 100 | 3.3
2025-07-03 | 100 | 3.3
2025-07-04 | 100 | 3.3
2025-07-05 | 100 | 3.3
2025-07-06 | 100 | 3.3
2025-07-07 | 100 | 3.3
2025-07-08 | 100 | 3.3
2025-07-09 | 100 | 3.3
2025-07-10 | 100 | 3.3
2025-07-11 | 100 | 3.3
2025-07-12 | 100 | 3.3
2025-07-13 | 100 | 3.3
2025-07-14 | 100 | 3.3
2025-07-15 | 100 | 3.3
2025-07-16 | 100 | 3.3
2025-07-17 | 100 | 3.3
2025-07-18 | 100 | 3.3
2025-07-19 | 100 | 3.3
2025-07-20 | 100 | 3.3
2025-07-21 | 100 | 3.3
2025-07-22 | 100 | 3.3
2025-07-23 | 100 | 3.3
2025-07-24 | 100 | 3.3
2025-07-25 | 100 | 3.3
2025-07-26 | 100 | 3.3
2025-07-27 | 100 | 3.3
2025-07-28 | 100 | 3.3
2025-07-29 | 100 | 3.3
2025-07-30 | 100 | 3.3
2025-07-31 | 100 | 3.3

## Remaining
Issue ID | Corridor | Description | Status
1 | East | TITAS 400mm explosive test | Pending
2 | East | TITAS 200mm explosive test | Pending
3 | East | TITAS shutdown & commissioning | Pending

## Issue Log
Issue ID | Corridor | Description | Status | Created on | Resolved on
1 | East | Delay in excavation due to rain | Pending | 2025-01-02 | 2025-02-02
2 | West | Gas pipe leakage detected | Solved | 2025-01-03 | 2025-02-03
3 | Cross | Water supply pipe damaged | Pending | 2025-01-04 | 2025-02-04
4 | East | Equipment shortage | Pending | 2025-01-05 | 2025-02-05
5 | West | Gas pipe installation complete | Solved | 2025-01-06 | 2025-02-06

## images
image | update_date
s05/plan.jpg | 2025-04-10
s05/HA1-HA1'.jpg | 2025-04-10
s05/HA2-HA2'.jpg | 2025-04-10
s05/HA3-HA3'.jpg | 2025-04-10
s05/HA4-HA4'.jpg | 2025-04-10
s05/C12-C12'.jpg | 2025-04-10
s05/C13-C13'.jpg | 2025-04-10
s05/C13A-C13A'.jpg | 2025-04-10
s05/C13B-C13B'.jpg | 2025-04-10